## Sayfa1
Title | Description
Project Name | To-Do List Application (Web-Based)
Project Purpose | To develop a system that allows users to add, edit, delete, and mark tasks as completed.
Additional Outcomes | Demonstrating teamwork, project planning, and task management processes using Jira alongside software development.
Estimated Duration | 6 Weeks Total
Total Workload | 120 Hours (40 hours per member)
Full Name | Role in Project | Task Description
Ömer Saydamoğlu | Project Manager & Frontend Developer | Project tracking, UI design, and connecting Frontend to Backend APIs.
Nazlım Aynacı | Backend Developer | Setting up the system architecture with Spring Boot, database management, and writing CRUD APIs.
Talha Soydaş | System Analyst & Integration Developer | Analyzing system requirements, drawing UML diagrams, end-to-end testing, and system integration.
Week | Phase | Tasks (To-Do)
Week 1 | Planning & Setup | Project idea finalization, role distribution, Jira setup, GitHub repository creation, project structure planning.
Week 2 | Backend Foundation | Spring Boot project setup, database configuration (MySQL), entity classes (User, Task), repository layer implementation.
Week 3 | Backend Development | CRUD API development, Login & Register endpoints, basic authentication setup, API testing with Postman.
Week 4 | Frontend Development | UI design, Login/Register pages, Task list page, connecting frontend to backend APIs.
Week 5 | Integration & Testing | Frontend-Backend integration, system testing, bug fixing, Jira issue tracking updates.
Week 6 | Finalization & Submission | Final testing, UML diagram completion, documentation writing, final upload to GitHub, submission on UBIS.
Resource Type | Detail / Technology | Assigned Person / Amount | Estimated Duration / Cost
Human Resource | Project Management and Frontend Development | Ömer Saydamoğlu | 40 Hours
Human Resource | Backend Development (Spring Boot, Hibernate) | Nazlım Aynacı | 40 Hours
Human Resource | Analysis, Integration, and Testing | Talha Soydaş | 40 Hours
Time Resource | Total Project Duration | Whole Team | 6 Weeks (120 Hours Total)
Software & Technology | Frontend: HTML, CSS, JavaScript | Ömer Saydamoğlu | Free / Open Source
Software & Technology | Backend: Spring Boot, Hibernate (JPA) | Nazlım Aynacı | Free / Open Source
Software & Technology | Database: MySQL | Whole Team | Free / Open Source
Tools & Management | Version Control (GitHub), Task Management (Jira) | Whole Team | Free Versions
Tools & Management | Communication (Google Teams), Design (Draw.io / PlantUML) | Whole Team | Free Versions