## Sayfa1
Member Name | Role | Responsibilities
Ömer Saydamoğlı | Project Manager & Backend | Project planning, backend logic
Nazlım Aynacı | Frontend Developer & UI/UX | Interface design, styling
Talha Soydaş | System Analyst & Integration | Requirement analysis, integration
Project Title | To-Do List Application
Objective | Develop a web-based task management system
Technologies | HTML, CSS, JavaScript
Tools Used | Jira, GitHub, Google Teams
Duration | 6 Weeks
Week | Activities | Responsible Member
Week 1 | Requirement analysis & planning | All Members
Week 2 | UML Diagram & system design | Talha Soydaş
Week 3 | Frontend development | Nazlım Aynacı
Week 4 | Backend implementation | Ömer Saydamoğlı
Week 5 | Integration & testing | All Members
Week 6 | Final revisions & submission | All Members
Member | Estimated Hours | Hourly Effort (%)
Ömer Saydamoğlı | 40 | 33%
Nazlım Aynacı | 40 | 33%
Talha Soydaş | 40 | 33%
Total | 120 Hours | 100%
Resource | Purpose | Cost
Jira | Task Management | Free (Student)
GitHub | Version Control | Free
Google Teams | Communication | Free
Draw.io | UML Diagram | Free